## 变更履历
LRDS106 FW变更履历
序号 | 日期 | 变更提出人 | 版本 | 阶段 | 变更原因 | 变更内容 | 附件 | 备注
1 | 2022-01-24 | 徐震 | V1.7.1.2 | 运维 | 1.解决所有功能无法使用问题 2.解决wifi断开连接后无法重连问题 | [BugFix]No:TLB-master-V1.7.1-1 BugNo: XXXXXX XXXXXX Modifier: Jin.Xu Time: 2022/1/24 Modify Files: camera/sample/main.c camera/sample/tuya/demo/src/tuya_ipc_wifi_demo.c system/babycam/system/init/app_init.sh system/babycam/system/init/Debug/app_init.sh system/babycam/system/init/Debug/app_init_debug.sh Symbol: 1.所有功能无法使用 2.wifi断开连接后无法重连 Reason: 1.media_sample进程退出 2.没有wifi断连后重连机制 Solution: 1.添加守护进程“media_sample save”守护media_sample进程，当media_sample进程退出时重启设备 2.添加wifi断连后重连机制，首次连接wifi后每隔30秒检查与tuya的连通情况，无法连通则重新获取Ip，持续6分钟无法连通则重启设备 | （RD自测报告）
2 | 2022-01-26 | 胡家乐 | V1.7.1.3 |  | 1。解决OTA无法支持文件修改的问题 2.解决异常重启影响用户体验的问题 | [BugFix]No:TLB-master-V1.7.1-2 Modifier: Joe.Hu Time: 2022/1/26 Modify Files: camera/common/include/comm_def.h camera/hal/motor/src/lux_hal_motor.c camera/modules/media/include/lux_base.h camera/modules/media/src/lux_base.c camera/modules/media/src/lux_fsrc.c camera/modules/media/src/lux_nv2jpeg.c camera/sample/ingenic/src/sample-Encoder-video.c camera/sample/main.c camera/sample/tuya/demo/src/tuya_ipc_sd_demo.c camera/sample/tuya/demo/src/tuya_ipc_system_control_demo.c Camera/sample/tuya/demo/src/user_main.c system/babycam/system/init/Debug/app_init.sh system/babycam/system/init/Debug/app_init_debug.sh system/babycam/system/init/app_init.sh system/babycam/system/init/backup/factory_reset.sh Symbol: 1.设备重启位置回归初始位置 2.OTA设备设备不支持新增功能 3.异常重启的语音播报会强化用户对重启的感知 Reason: 1.未记忆电机转动位置 2.文件修改无法同步OTA 3.需要关闭异常重启的语音播报 Solution: 1.记录电机转动位置，启动时转动到记忆位置 2.OTA升级后修改相关文件 3.异常重启后增加标识文件，存在标识文件时不播报开机语音
3 | 2022-02-09 | 徐震 | V1.7.2 | 运维 | 1.优化wifi断线未重连重启设备时间：6分针==>4分钟 | [BugFix]No:TLB-master-V1.7.2-1 BugNo: XXXXXX XXXXXX Modifier: Jin.Xu Time: 2022/2/9 Modify Files: camera/sample/main.c camera/sample/tuya/demo/src/user_main.c Symbol: 1.wifi断线未重连重启设备时间过长 Reason: 1.wifi断线未重连重启设备时间过长 Solution: 1.优化wifi断线未重连重启设备时间：6分针==>4分钟 |  | 测试步骤： 正常连接后关闭路由器 测试结果： 关闭路由器4分钟后设备重启
4 | 2022-02-11 | 胡家乐 | V1.7.2.2 | 运维 | 减少用户模式下的串口信息打印 | [BugFix]No:TLB-master-V1.7.2.2 Modifier: Joe.Hu Time: 2022/2/11 Modify Files: camera/common/include/comm_def.h Camera/sample/tuya/demo/src/user_main.c system/babycam/system/init/backup/factory_reset.sh system/babycam/system/init/Debug/Debug.sh system/babycam/system/init/Debug/Normal.sh Symbol: 1.减少用户模式下，因过量日志信息而导致的CPU负担 Reason: 1.减少用户模式下，因过量日志信息而导致的CPU负担 Solution: 1.修改默认情况下涂鸦 日志 级别为0 2.Debug模式下日志级别为4，并且可通过修改/system/init/Debug/IsDebug文件中的数值，调整日志数量[0~5]
5 | 2022-02-16 | 胡家乐 | V1.7.2.3 | 运维 | 替换哭声侦测lib文件 | [BugFix]No:TLB-master-V1.7.2.3 Modifier: Joe.Hu Time: 2022/2/11 Modify Files: camera/libs/ingenic/alg/libcryDet_inf.so camera/libs/ingenic/alg/libjzdl.so camera/sample/main.c camera/sample/tuya/demo/src/user_main.c system/babycam/system/lib/libcryDet_inf.so system/babycam/system/lib/libjzdl.so Symbol: 1.替换哭声侦测lib文件 Reason: 1.哭声侦测灵敏度较低 Solution: 1.替换君正提供新版哭声侦测SDK Ingenic-ADKV2-7aa35cc-202202141506.7z
6 | 2/17/2022 | 徐保权 | V1.8.0 | 运维 | 发布正式版本 | [BugFix]No:TLB-master-V1.8.0 Modifier: Baoquan.Xu Time: 2022/2/17 Modify Files: camera/sample/tuya/demo/src/user_main.c Symbol: 1.更新版本号 Reason: 1.发布新版本1.8.0 Solution: 1.更新版本号
7 | 2022-02-18 | 徐震 | V1.8.1 | 运维 | 1.关闭掉线重连机制，也不会重启 | [BugFix]No:TLB-master-V1.8.1-1 BugNo: XXXXXX XXXXXX Modifier: Jin.Xu Time: 2022/2/18 Modify Files: camera/sample/main.c camera/sample/tuya/demo/src/user_main.c Symbol: 1.海外地区设备开机4分钟后重启 Reason: 1.海外地区无法ping通域名www.tuya.com Solution: 1.关闭掉线重连机制，也不会重启 | （RD自测报告）
8 | 2022-02-21 | 徐震 | V1.8.1.1 | 运维 | 1.添加media_sample进程接收到SIGPIP信号后打印信号类型和信号值，发送信号的线程id，发送信号的线程名的debug，并忽略该信号原始处理 | [BugFix]No:TLB-master-V1.8.1.1-1 BugNo: XXXXXX XXXXXX Modifier: Jin.Xu Time: 2022/2/21 Modify Files: camera/sample/main.c camera/sample/tuya/demo/src/user_main.c Symbol: 1.反复操作进出观看直播后media_sample进程退出 Reason: 1.tuya_p2p线程在tcp socket异常断开时会发送SIGPIPE信号终止media_sample进程 Solution: 1.添加media_sample进程接收到SIGPIP信号后打印信号类型和信号值，发送信号的线程id，发送信号的线程名的debug，并忽略该信号原始处理 | （RD自测报告）
9 | 2022-02-22 | 胡家乐 | V1.8.1.2 | 运维 | 1.增加英文版语音资料 2.移除弃用语音 | [BugFix]No:TLB-master-V1.8.1.2-1 BugNo: XXXXXX XXXXXX Modifier: Joe.Hu Time: 2022/2/22 Modify Files: modified: camera/sample/mk modified: camera/sample/tuya/demo/src/user_main.c modified: system/babycam/cam_baby.img modified: system/babycam/system.jffs2 deleted: system/babycam/system/bin/audio/danger_keep_away.pcm deleted: system/babycam/system/bin/audio/please_leave.pcm deleted: system/babycam/system/bin/audio/welcome.pcm modified: system/babycam/system/bin/media_sample Add: system/babycamEU/ Symbol: 1.增加制作英文版镜像编译文件 2.移除无用语言资料节省内存空间 Reason: 1.增加英文版语音资料 2.移除弃用语音 Solution: 1.增加英文版语音资料 2.移除弃用语音 | （RD自测报告）
10 | 2022-02-24 | 胡家乐 | V1.8.2 | 运维 | 发布正式版本 | [BugFix]No:TLB-master-V1.8.2-1 BugNo: XXXXXX XXXXXX Modifier: Joe.Hu Time: 2022/2/24 Modify Files: modified: camera/sample/mk modified: system/babycamEU/babycamEU/mk Symbol: 1.发布正式版本 2.编译脚本便利性修改 Reason: 1.发布正式版本 2.编译脚本便利性修改 Solution: 1.发布正式版本 2.编译脚本便利性修改 | （RD自测报告）
11 | 2022-02-28 | 胡家乐 | V1.8.2.1 | 运维 | 调试信息增加观看用户数量变化 | [BugFix]No:TLB-master-V1.8.2.1-1 BugNo: XXXXXX XXXXXX Modifier: Joe.Hu Time: 2022/2/28 Modify Files: camera/sample/tuya/demo/src/user_main.c Symbol: 1.调试信息增加观看用户数量变化 Reason: 1.调试信息增加观看用户数量变化 Solution: 1.调试信息增加观看用户数量变化
12 | 2022-02-28 | 胡家乐 | V1.8.2.2 | 运维 | 解决隐私模式下，无实际录像，但回看显示有记录的问题 | [BugFix]No:TLB-master-V1.8.2.2-1 BugNo: XXXXXX XXXXXX Modifier: Joe.Hu Time: 2022/2/28 Modify Files: camera/sample/tuya/demo/src/user_main.c Symbol: 1.开启隐私模式后一段时间关闭，显示回看有记录，但实际不可播放 Reason: 1.隐私模式开启时时，RingBuffer中数据更新停止。 关闭隐私模式时，RingBuffer中有部分之前时间节点的数据 被记录到SD卡中，造成程序误以为还在录制 Solution: 1.隐私模式下也保持RingBuffer数据更新
13 | 2022-03-07 | 廖威 | V1.8.2.3 | 运维 | 更新tuya sdk版本 4.9.14 | [BugFix]No:TLB-master-V1.8.2.3-1 BugNo: XXXXXX XXXXXX Modifier: Wei Liao Time: 2022/3/7 Modify Files: camera/libs/tuya/libmbedtls.a camera/libs/tuya/libtuya_ipc.a camera/sample/tuya/demo/src/user_main.c camera/sample/tuya/include/tuya_cloud_com_defs.h camera/sample/tuya/include/tuya_cloud_error_code.h camera/sample/tuya/include/tuya_cloud_wifi_defs.h camera/sample/tuya/include/tuya_iot_config.h camera/sample/tuya/include/tuya_ipc_ai_detect_storage.h camera/sample/tuya/include/tuya_ipc_api.h camera/sample/tuya/include/tuya_ipc_cloud_storage.h camera/sample/tuya/include/tuya_ipc_media.h camera/sample/tuya/include/tuya_ipc_mqt_proccess.h camera/sample/tuya/include/tuya_ipc_p2p.h camera/sample/tuya/include/tuya_ipc_skill.h camera/sample/tuya/include/tuya_ipc_stream_storage.h camera/sample/tuya/include/tuya_ipc_voice.h camera/sample/tuya/include/tuya_ipc_webrtc.h camera/sample/tuya/include/tuya_ring_buffer.h camera/sample/tuya/include/uni_network.h Symbol: 1.更新tuya SDK V4.9.14 Reason: 1.更新tuya SDK V4.9.14 Solution: 1.更新tuya SDK V4.9.14
14 | 2022-03-11 | 廖威 | V1.8.2.4 | 运维 | 使用人脸识别算法实现遮脸检测功能 | [BugFix]No:TLB-master-V1.8.2.4-1 BugNo: XXXXXX XXXXXX Modifier: Wei Liao Time: 2022/3/11 Modify Files: camera/libs/ingenic/alg/libfaceDet_inf.a camera/libs/ingenic/alg/libfaceDet_inf.so camera/modules/ingenic/alg/include/ivs_inf_faceDet.h camera/modules/ingenic/ivs/include/ivs_inf_faceDet.h camera/modules/media/include/lux_coverFace.h camera/modules/media/include/lux_smileDet.h camera/modules/media/src/lux_coverFace.c camera/modules/media/src/lux_ivs.c camera/modules/media/src/lux_smileDet.c camera/sample/Makefile camera/sample/tuya/demo/src/tuya_ipc_dp_handler.c camera/sample/tuya/demo/src/user_main.c system/babycam/system/lib/libfaceDet_inf.so system/babycamEU/system/lib/libfaceDet_inf.so Symbol: 1.使用人脸识别算法实现遮脸检测功能 Reason: 1.使用人脸识别算法实现遮脸检测功能 Solution: 1.使用人脸识别算法实现遮脸检测功能
15 | 2022-03-21 | 徐保权 | V1.8.2.7 | 运维 | 增加童谣、定制语音功能 | [BugFix]No:TLB-master-V1.8.2.7 BugNo: XXXXXX XXXXXX Modifier: Baoquan.Xu Time: 2022/3/21 Modify Files: camera/modules/media/src/lux_audio.c camera/sample/tuya/demo/inc/tuya_ipc_dp_handler.h camera/sample/tuya/demo/inc/tuya_ipc_dp_utils.h camera/sample/tuya/demo/src/tuya_ipc_dp_handler.c camera/sample/tuya/demo/src/tuya_ipc_dp_utils.c camera/sample/tuya/demo/src/tuya_ipc_p2p_demo.c camera/sample/tuya/demo/src/tuya_ipc_system_control_demo.c system/babycam/system/init/tuya_config.ini system/babycam/system/init/backup/tuya_config.ini system/babycamEU/system/init/tuya_config.ini system/babycamEU/system/init/backup/tuya_config.ini Symbol: 1.增加童谣、定制语音功能 Reason: 1.S1_Pro需求 Solution: 1.增加童谣、定制语音功能
16 | 2022-03-23 | 徐保权 | V1.8.2.7 | 运维 | 优化功能 | [BugFix]No:TLB-master-V1.8.2.7-2 BugNo: XXXXXX XXXXXX Modifier: Baoquan.Xu Time: 2022/3/23 Modify Files: camera/sample/tuya/demo/inc/tuya_ipc_dp_handler.h camera/sample/tuya/demo/src/tuya_ipc_dp_handler.c camera/sample/tuya/demo/src/tuya_ipc_dp_utils.c Symbol: 1.优化功能 Reason: 1.S1_Pro需求 Solution: 1.优化功能
17 | 2022-03-23 | 胡家乐 | V1.8.4.1 | 运维 | 开放音量调节 降低提示音文件声音大小 增加调节提示音 禁用一些不会用到的代码 调整算法初始化位置 Debug模式不再打开watchdog | [BugFix]No:TLB-master-V1.8.4-1 BugNo: XXXXXX XXXXXX Modifier: Joe Hu Time: 2022/3/23 Modify Files: camera/modules/media/src/lux_audio.c camera/modules/media/src/lux_isp.c camera/modules/media/src/lux_ivs.c camera/modules/media/src/lux_nv2jpeg.c camera/sample/tuya/demo/inc/tuya_ipc_dp_utils.h camera/sample/tuya/demo/inc/tuya_ipc_system_control_demo.h camera/sample/tuya/demo/src/tuya_ipc_dp_handler.c camera/sample/tuya/demo/src/tuya_ipc_dp_utils.c camera/sample/tuya/demo/src/tuya_ipc_system_control_demo.c camera/sample/tuya/demo/src/user_main.c system/babycam/system/bin/audio/blessing.pcm system/babycam/system/bin/audio/connect_ok.pcm system/babycam/system/bin/audio/scan_ok.pcm system/babycam/system/bin/audio/wait_conn.pcm system/babycam/system/bin/audio/ding.pcm system/babycam/system/init/Debug/app_init_debug.sh system/babycam/system/init/backup/tuya_config.ini system/babycam/system/init/tuya_config.ini system/babycam/system/bin/audio/ding.pcm Symbol: 优化用户体验 优化代码结构 Reason: 优化代码结构 Solution: 1.开放音量调节 2.降低提示音文件声音大小 3.禁用一些用不到的代码 4.调整算法初始化位置 5.Debug模式不再打开watchdog
| 2022-03-28 | 胡家乐 | V1.8.4.2 | 运维 | 优化哭声算法 | [BugFix]No:TLB-master-V1.8.4.2-1 BugNo: XXXXXX XXXXXX Modifier: Joe Hu Time: 2022/3/23 Modify Files: Camera/libs/ingenic/alg/libcryDet_inf.so camera/modules/media/src/lux_audio.c camera/sample/tuya/demo/src/user_main.c system/babycam/system/lib/libcryDet_inf.so Symbol: 优化哭声算法 Reason: 优化哭声算法 Solution: 优化哭声算法 打印哭声次数
19 | 2022-03-29 | 徐保权 | V1.8.5.1 | 运维 | 增加暂停、切换音频功能 | [BugFix]No:TLB-master-V1.8.5.1 BugNo: XXXXXX XXXXXX Modifier: Baoquan Xu Time: 2022/3/29 Modify Files: camera/sample/tuya/demo/inc/tuya_ipc_dp_handler.h camera/sample/tuya/demo/src/tuya_ipc_dp_handler.c camera/sample/tuya/demo/src/tuya_ipc_dp_utils.c camera/sample/tuya/demo/src/tuya_ipc_wifi_demo.c camera/sample/tuya/demo/src/tuya_ipc_system_control_demo.c camera/sample/tuya/demo/src/user_main.c Symbol: 增加暂停、切换音频功能 Reason: S1_Pro需求 Solution: 增加暂停、切换音频功能
19 | 2022-03-31 | 徐保权 | V1.8.5.2 | 运维 | 功能优化 | [BugFix]No:TLB-master-V1.8.5.2 BugNo: XXXXXX XXXXXX Modifier: Baoquan Xu Time: 2022/3/31 Modify Files: camera/modules/media/src/lux_audio.h camera/modules/media/src/lux_audio.c camera/sample/tuya/demo/src/tuya_ipc_dp_handler.c camera/sample/tuya/demo/src/tuya_ipc_system_control_demo.c camera/sample/tuya/demo/src/user_main.c Symbol: 功能优化 Reason: S1_Pro需求 Solution: 功能优化
20 | 2022-04-06 | 胡家乐 | V1.8.5.3 | 运维 | 功能增加 | [BugFix]No:TLB-master-V1.8.5.3 BugNo: XXXXXX XXXXXX Modifier: Joe.Hu Time: 2022/4/6 Modify Files: camera/common/include/comm_def.h camera/modules/media/include/lux_audio.h camera/modules/media/include/lux_base.h camera/modules/media/include/lux_coverFace.h camera/modules/media/include/lux_ivs.h camera/modules/media/include/lux_perm.h camera/modules/media/include/lux_sleepDet.h camera/modules/media/src/lux_audio.c camera/modules/media/src/lux_base.c camera/modules/media/src/lux_coverFace.c camera/modules/media/src/lux_event.c camera/modules/media/src/lux_ivs.c camera/modules/media/src/lux_perm.c camera/modules/media/src/lux_sleepDet.c camera/modules/media/src/lux_smileDet.c camera/sample/tuya/demo/inc/tuya_ipc_dp_handler.h camera/sample/tuya/demo/inc/tuya_ipc_dp_utils.h camera/sample/tuya/demo/inc/tuya_ipc_system_control_demo.h camera/sample/tuya/demo/src/tuya_ipc_dp_handler.c camera/sample/tuya/demo/src/tuya_ipc_dp_utils.c camera/sample/tuya/demo/src/tuya_ipc_system_control_demo.c camera/sample/tuya/demo/src/user_main.c system/babycam/system/init/backup/factory_reset.sh system/babycam/system/init/backup/tuya_config.ini system/babycam/system/init/tuya_config.ini Symbol: 增加多边形区域检测 增加睡眠检测部分功能 记录7天内事件时间 调整遮脸检测代码逻辑 调整人形检测代码逻辑 调整音量调节逻辑 调整首次时间同步代码位置 Reason: S1_Pro需求 Solution: 功能优化
21 | 2022-04-07 | 胡家乐 | V1.8.5.3 | 运维 | 更新uImage和WIFI驱动 更新EU版文件夹 | [BugFix]No:TLB-master-V1.8.5.3-2 BugNo: XXXXXX XXXXXX Modifier: Joe.Hu Time: 2022/4/7 Modify Files: modified: system/babycam/system/init/Debug/app_init.sh modified: system/babycam/system/init/Debug/app_init_debug.sh modified: system/babycam/system/init/app_init.sh modified: system/babycam/system/ko/8189fs.ko modified: system/babycam/uImage new file: system/babycam/uImage...default new file: system/babycamEU/system/bin/audio/ding.pcm modified: system/babycamEU/system/init/Debug/app_init.sh modified: system/babycamEU/system/init/Debug/app_init_debug.sh modified: system/babycamEU/system/init/app_init.sh modified: system/babycamEU/system/init/backup/factory_reset.sh modified: system/babycamEU/system/init/backup/tuya_config.ini modified: system/babycamEU/system/init/tuya_config.ini modified: system/babycamEU/system/ko/8189fs.ko modified: system/babycamEU/system/lib/libcryDet_inf.so modified: system/babycamEU/uImage new file: system/babycamEU/uImage...default Symbol: 优化WIFI稳定性驱动 更新EU版文件夹 Reason: 功能优化 Solution: 功能优化
22 | 2022-04-08 | 徐保权 | V1.8.5.4 | 运维 | 优化音频播放及音量调节 | [BugFix]No:TLB-master-V1.8.5.4 BugNo: XXXXXX XXXXXX Modifier: Baoquan Xu Time: 2022/4/9 Modify Files: camera/modules/media/src/lux_audio.c camera/sample/tuya/demo/src/tuya_ipc_dp_handler.c camera/sample/tuya/demo/src/tuya_ipc_dp_utils.c camera/sample/tuya/demo/src/tuya_ipc_system_control_demo.c camera/sample/tuya/demo/src/user_main.c Symbol: 优化音频播放及音量调节 Reason: S1_Pro需求 Solution: 优化音频播放及音量调节
23 | 2022-04-11 | 胡家乐 | V1.8.5.5 | 运维 | 完善睡眠检测 完善统计功能 隐藏watchdog打印 调整时间戳代码逻辑 | [BugFix]No:TLB-master-V1.8.5.5 BugNo: XXXXXX XXXXXX Modifier: Joe Hu Time: 2022/4/11 Modify Files: modified: camera/modules/media/include/lux_base.h new file: camera/modules/media/include/lux_summary.h modified: camera/modules/media/src/lux_audio.c modified: camera/modules/media/src/lux_base.c modified: camera/modules/media/src/lux_coverFace.c modified: camera/modules/media/src/lux_event.c modified: camera/modules/media/src/lux_osd.c modified: camera/modules/media/src/lux_sleepDet.c modified: camera/modules/media/src/lux_smileDet.c new file: camera/modules/media/src/lux_summary.c modified: camera/modules/media/src/lux_video.c modified: camera/sample/tuya/demo/inc/tuya_ipc_dp_handler.h modified: camera/sample/tuya/demo/inc/tuya_ipc_dp_utils.h modified: camera/sample/tuya/demo/src/tuya_ipc_dp_handler.c modified: camera/sample/tuya/demo/src/tuya_ipc_dp_utils.c modified: camera/sample/tuya/demo/src/tuya_ipc_system_control_demo.c modified: camera/sample/tuya/demo/src/user_main.c modified: system/babycam/system/init/Debug/app_init.sh modified: system/babycam/system/init/app_init.sh modified: system/babycamEU/system/init/Debug/app_init.sh modified: system/babycamEU/system/init/app_init.sh Symbol: 完善睡眠检测 完善统计功能 隐藏watchdog打印 调整时间戳代码逻辑 Reason: 功能优化 Solution: 功能优化
24 | 2022-04-12 | 陈湘杰 | V1.8.5.6 | 运维 | OTA升级修改 | [BugFix]No:TLB-master-V1.8.5.6 BugNo: XXXXXX XXXXXX Modifier: Xiangjie Chen Time: 2022/4/12 Modify Files: modified: camera/sample/tuya/demo/src/tuya_ipc_system_control_demo.c modified: camera/sample/tuya/demo/src/user_main.c Symbol: OTA升级修改 Reason: 功能优化 Solution: 功能优化
25 | 2022-04-15 | 胡家乐 | V1.8.5.7 | 运维 | 增加wifi 登陆无密码支持 增加电机源码 | [BugFix]No:TLB-master-V1.8.5.7 BugNo: XXXXXX XXXXXX Modifier: Joe.Hu Time: 2022/4/15 Modify Files: modified: camera/sample/tuya/demo/src/tuya_ipc_wifi_demo.c modified: camera/sample/tuya/demo/src/user_main.c Symbol: 增加wifi 登陆无密码支持 Reason: 功能优化 Solution: 功能优化
26 | 2022-04-16 | 徐保权 | V1.8.5.8 | 运维 | 音频功能优化 | [BugFix]No:TLB-master-V1.8.5.8 BugNo: XXXXXX XXXXXX Modifier: Baoquan Xu Time: 2022/4/16 Modify Files: system/etc/mdev/sd_insert.sh system/etc/mdev/sd_remove.sh camera/modules/media/src/lux_audio.c camera/sample/tuya/demo/src/tuya_ipc_dp_handler.c camera/sample/tuya/demo/src/tuya_ipc_p2p_demo.c camera/sample/tuya/demo/src/tuya_ipc_system_control_demo.c camera/sample/tuya/demo/src/user_main.c Symbol: 音频功能优化 Reason: S1_Pro需求 Solution: 音频功能优化
27 | 2022-04-21 | 徐保权 | V1.8.6 | 运维 | 音频功能优化 | [BugFix]No:TLB-master-V1.8.6 BugNo: XXXXXX XXXXXX Modifier: Baoquan Xu Time: 2022/4/21 Modify Files: camera/sample/tuya/demo/src/tuya_ipc_system_control_demo.c camera/sample/tuya/demo/src/user_main.c Symbol: 音频功能优化 Reason: S1_Pro需求 Solution: 音频功能优化
28 | 2022-04-22 | 徐保权 | V1.8.7 | 运维 | 更改权限 | [BugFix]No:TLB-master-V1.8.7 BugNo: XXXXXX XXXXXX Modifier: Baoquan Xu Time: 2022/4/22 Modify Files: system/etc/mdev/sd_insert.sh system/etc/mdev/sd_remove.sh camera/sample/tuya/demo/src/user_main.c Symbol: 更改权限 Reason: S1_Pro需求 Solution: 更改权限
29 | 2022-04-22 | 陈湘杰 | V1.8.7 | 运维 | 更新wifi驱动 更新哭声侦测动态库 | [BugFix]No:TLB-master-V1.8.7 BugNo: XXXXXX XXXXXX Modifier: Xiangjie Chen Time: 2022/4/22 Modify Files: modified: camera/libs/ingenic/alg/libcryDet_inf.so modified: camera/libs/ingenic/alg/libjzdl.so modified: system/babycam/system/ko/8189fs.ko modified: system/babycam/system/lib/libcryDet_inf.so modified: system/babycam/system/lib/libjzdl.so modified: system/babycamEU/system/ko/8189fs.ko modified: system/babycamEU/system/lib/libcryDet_inf.so modified: system/babycamEU/system/lib/libjzdl.so Symbol: 更新wifi驱动 更新哭声侦测动态库 Reason: 功能优化 Solution: 功能优化
30 | 2022-04-22 | 刘光雨 | V1.8.7.1 | 运维 | 1.Sync kernel uImage same as master branch; 2.fix motor speed ioctl error in CalibrationProcess | [BugFix]No:TLB-master-V1.8.7.1 BugNo: XXXXXX XXXXXX Modifier: liuguangyu Time: 2022/4/22 Modify Files: camera/hal/motor/src/lux_hal_motor.c camera/out/media_sample.bin camera/sample/tuya/demo/src/user_main.c system/babycam/cam_baby - v1.8.7.1.img system/babycam/cam_baby.img system/babycam/system.jffs2 system/babycam/system/bin/media_sample system/babycam/uImage system/babycamEU/system/bin/media_sample system/babycamEU/uImage Symbol: 1.Sync kernel uImage same as master branch; 2.fix motor speed ioctl error in CalibrationProcess Reason: 功能优化 Solution: 功能优化
31 | 2022-04-25 | 陈湘杰 | V1.8.7.2 | 运维 | 1.还原哭声动态侦测库 | [BugFix]No:TLB-master-V1.8.7.2 BugNo: XXXXXX XXXXXX Modifier: Xiangjie Time: 2022/4/25 Modify Files: modified: camera/libs/ingenic/alg/libcryDet_inf.so modified: camera/libs/ingenic/alg/libjzdl.so modified: camera/sample/tuya/demo/src/tuya_ipc_wifi_demo.c modified: camera/sample/tuya/demo/src/user_main.c modified: system/babycam/system/lib/libcryDet_inf.so modified: system/babycam/system/lib/libjzdl.so modified: system/babycamEU/system/lib/libcryDet_inf.so modified: system/babycamEU/system/lib/libjzdl.so Symbol: 1.还原哭声动态侦测库 Reason: 功能优化 Solution: 功能优化
32 | 2022-04-27 | 陈湘杰 | V2.0.0.1 | 运维 | 1.优化睡眠监测和统计数据功能 | [BugFix]No:TLB-master-V2.0.0.1 BugNo: XXXXXX XXXXXX Modifier: Xiangjie Time: 2022/4/27 Modify Files: modified: camera/modules/media/src/lux_sleepDet.c modified: camera/modules/media/src/lux_summary.c modified: camera/sample/tuya/demo/src/tuya_ipc_dp_handler.c modified: camera/sample/tuya/demo/src/tuya_ipc_dp_utils.c modified: camera/sample/tuya/demo/src/user_main.c Symbol: 1.优化睡眠监测和统计数据功能 Reason: 功能优化 Solution: 功能优化
33 | 2022-04-28 | 陈湘杰 | V2.0.0.2 | 运维 | 1.优化睡眠监测 2.修复北美版SD卡挂载问题 | [BugFix]No:TLB-master-V2.0.0.2 BugNo: XXXXXX XXXXXX Modifier: Xiangjie Time: 2022/4/27 Modify Files: modified: camera/modules/media/src/lux_sleepDet.c modified: camera/sample/tuya/demo/src/user_main.c modified: system/babycamEU/system/etc/mdev/sd_insert.sh modified: system/babycamEU/system/etc/mdev/sd_remove.sh Symbol: 1.优化睡眠监测 2.修复北美版SD卡挂载问题 Reason: 功能优化 Solution: 功能优化
34 | 2022-04-28 | 胡家乐 | V2.0.0.3 | 运维 | 1.优化自定义安抚音 | [BugFix]No:TLB-master-V2.0.0.3 BugNo: XXXXXX XXXXXX Modifier: Joe Hu Time: 2022/4/28 Modify Files: modified: camera/modules/media/src/lux_audio.c modified: camera/sample/tuya/demo/inc/tuya_ipc_system_control_demo.h modified: camera/sample/tuya/demo/src/tuya_ipc_dp_handler.c modified: camera/sample/tuya/demo/src/tuya_ipc_p2p_demo.c modified: camera/sample/tuya/demo/src/tuya_ipc_system_control_demo.c modified: camera/sample/tuya/demo/src/user_main.c Symbol: 1.优化自定义安抚音,替换时无需重启 Reason: 功能优化 Solution: 功能优化
35 | 2022-04-28 | 陈湘杰 | V2.0.0.4 | 运维 | 1.优化数据统计功能 | [BugFix]No:TLB-master-V2.0.0.4 BugNo: XXXXXX XXXXXX Modifier: Xiangjie Time: 2022/4/28 Modify Files: modified: camera/modules/media/src/lux_sleepDet.c modified: camera/modules/media/src/lux_summary.c modified: camera/sample/tuya/demo/src/user_main.c Symbol: 1.优化数据统计功能 Reason: 功能优化 Solution: 功能优化
36 | 2022-04-29 | 胡家乐 | V2.0.0.5 | 运维 | 1.修复安抚音不还原的问题 2.睡眠监测默认值设置为开启 | [BugFix]No:TLB-master-V2.0.0.5 BugNo: XXXXXX XXXXXX Modifier: Joe Hu Time: 2022/4/29 Modify Files: modified: camera/modules/media/src/lux_base.c modified: camera/sample/ingenic/src/sample-Encoder-video.c modified: camera/sample/tuya/demo/src/user_main.c modified: system/babycam/system/bin/media_sample modified: system/babycam/system/init/Debug/app_init.sh modified: system/babycam/system/init/Debug/app_init_debug.sh modified: system/babycam/system/init/app_init.sh modified: system/babycam/system/init/backup/factory_reset.sh modified: system/babycam/system/init/backup/tuya_config.ini modified: system/babycam/system/init/tuya_config.ini modified: system/babycamEU/system/bin/media_sample modified: system/babycamEU/system/init/Debug/app_init.sh modified: system/babycamEU/system/init/Debug/app_init_debug.sh modified: system/babycamEU/system/init/app_init.sh modified: system/babycamEU/system/init/backup/factory_reset.sh modified: system/babycamEU/system/init/backup/tuya_config.ini modified: system/babycamEU/system/init/tuya_config.ini new file: system/ota.zip new file: system/zip_ota.sh Symbol: 1.修复恢复出厂设置时，安抚音不还原的问题; 2.睡眠监测开关默认开启(待APP设置开关后默认关闭); 3.Media_sample不再对配置文件版本进行比较; 4.增加OTA打包示例 Reason: 功能优化 Solution: 功能优化
37 | 2022-05-03 | 胡家乐 | V2.0.0.6 | 运维 | 1.修复夜间模式光感失效问题 | [BugFix]No:TLB-master-V2.0.0.6 BugNo: XXXXXX XXXXXX Modifier: Joe Hu Time: 2022/5/3 Modify Files: modified: camera/sample/tuya/demo/src/user_main.c modified: system/babycam/system/etc/sensor/sc4238-t31.bin modified: system/babycamEU/system/etc/sensor/sc4238-t31.bin Symbol: 1.修复夜间模式光感失效问题 Reason: 功能优化 Solution: 功能优化
38 | 2022-05-04 | 胡家乐 | V2.0.0.7 | 运维 | 1.优化睡眠监测 2.调整睡眠状态记录方式 | [BugFix]No:TLB-master-V2.0.0.7 BugNo: XXXXXX XXXXXX Modifier: Joe Hu Time: 2022/5/4 Modify Files: modified: camera/sample/tuya/demo/src/user_main.c modified: system/babycam/system/etc/sensor/sc4238-t31.bin modified: system/babycamEU/system/etc/sensor/sc4238-t31.bin Symbol: 1.增加睡眠监测 对面部识别状态判断的时长 2.睡眠监测代码简化 3.入睡后定期记录sleepKeep状态，以减少重启对统计的影响 Reason: 功能优化 Solution: 功能优化
39 | 2022-05-09 | 胡家乐 | V2.0.0.8 | 运维 | 1.优化睡眠监测 | [BugFix]No:TLB-master-V2.0.0.8 BugNo: XXXXXX XXXXXX Modifier: Joe Hu Time: 2022/5/9 Modify Files: modified: camera/modules/media/src/lux_sleepDet.c modified: camera/sample/tuya/demo/src/user_main.c Symbol: 1.增加机制：长时间（约连续五分钟）无人脸+无运动情况下，停止睡眠统计（不上报） 2.入睡判断，将入睡阈值降低到0.1 ，增加入睡判断难度，减少误判 3.优化睡眠监测代码 Reason: 功能优化 Solution: 功能优化
40 | 2022-05-09 | 陈湘杰 | V2.0.0.9 | 运维 | 1.优化睡眠监测 | [BugFix]No:TLB-master-V2.0.0.9 BugNo: XXXXXX XXXXXX Modifier: Xiangjie Chen Time: 2022/5/9 Modify Files: modified: camera/modules/media/src/lux_sleepDet.c modified: camera/sample/tuya/demo/src/user_main.c Symbol: 1.优化睡眠监测，修改判断入睡和睡醒的移动次数阈值 Reason: 功能优化 Solution: 功能优化
41 | 2022-05-10 | 陈湘杰 | V2.0.0.10 | 运维 | 1.优化睡眠监测 | [BugFix]No:TLB-master-V2.0.0.10 BugNo: XXXXXX XXXXXX Modifier: Xiangjie Chen Time: 2022/5/10 Modify Files: modified: camera/modules/media/src/lux_summary.c modified: camera/sample/tuya/demo/src/user_main.c modified: system/babycam/system/init/backup/tuya_config.ini modified: system/babycam/system/init/tuya_config.ini modified: system/babycamEU/system/init/backup/tuya_config.ini modified: system/babycamEU/system/init/tuya_config.ini Modified: system/ota.zip Symbol: 1.优化睡眠监测代码，睡眠监测开关默认关闭 2.AA指令显示数据改为包括今天在内的7天总数据 Reason: 功能优化 Solution: 功能优化
42 | 2022-05-11 | 陈湘杰 | V2.0.0.11 | 运维 | 1.优化代码 | [BugFix]No:TLB-master-V2.0.0.11 BugNo: XXXXXX XXXXXX Modifier: Xiangjie Chen Time: 2022/5/11 Modify Files: modified: camera/common/include/comm_def.h modified: camera/modules/media/include/lux_nv2jpeg.h modified: camera/modules/media/src/lux_audio.c modified: camera/modules/media/src/lux_base.c modified: camera/modules/media/src/lux_coverFace.c modified: camera/modules/media/src/lux_isp.c modified: camera/modules/media/src/lux_ivs.c modified: camera/modules/media/src/lux_nv2jpeg.c modified: camera/modules/media/src/lux_sleepDet.c modified: camera/modules/media/src/lux_smileDet.c modified: camera/sample/main.c modified: camera/sample/tuya/demo/src/tuya_ipc_dp_handler.c modified: camera/sample/tuya/demo/src/tuya_ipc_media_demo.c modified: camera/sample/tuya/demo/src/tuya_ipc_system_control_demo.c modified: camera/sample/tuya/demo/src/user_main.c Symbol: 1.优化睡眠监测代码，入睡时间不再使用临时睡眠开始时间参数，精确判定入睡时刻 2.优化项目代码，消除在编译过程中的出现的所有警告 Reason: 功能优化 Solution: 功能优化
43 | 2022-05-24 | 陈湘杰 | V2.1.0.1 | 运维 | 1.增加EU版IPC水印 | [BugFix]No:TLB-master-V2.1.0.1 BugNo: XXXXXX XXXXXX Modifier: Xiangjie Chen Time: 2022/5/24 Modify Files: modified: camera/modules/media/src/lux_osd.c modified: camera/sample/Makefile new file: camera/sample/ingenic/include/logodata_eu_106x58_bgra.h new file: camera/sample/ingenic/include/logodata_eu_382x88_bgra.h new file: camera/sample/ingenic/include/logodata_eu_436x236_bgra.h modified: camera/sample/mk modified: camera/sample/tuya/demo/src/user_main.c modified: system/babycam/system/bin/media_sample modified: system/babycamEU/system/bin/media_sample modified: system/ota.zip Symbol: 1.增加EU版IPC水印 Reason: 功能优化 Solution: 功能优化
44 | 2022-05-25 | 陈湘杰 | V2.1.1 | 运维 | 1.修改水印读取方式，便于后期OTA升级维护 | [BugFix]No:TLB-master-V2.1.1 BugNo: XXXXXX XXXXXX Modifier: Xiangjie Chen Time: 2022/5/24 Modify Files: modified: camera/modules/media/src/lux_osd.c modified: camera/sample/Makefile deleted: camera/sample/ingenic/include/logodata_eu_106x58_bgra.h deleted: camera/sample/ingenic/include/logodata_eu_382x88_bgra.h deleted: camera/sample/ingenic/include/logodata_eu_436x236_bgra.h modified: camera/sample/mk modified: camera/sample/tuya/demo/src/user_main.c new file: system/PNG_to_Bin/.vscode/settings.json new file: system/PNG_to_Bin/Note_png2bin new file: system/PNG_to_Bin/eu/MOMWILIKE_106x58.png new file: system/PNG_to_Bin/eu/MOMWILIKE_382x88.png new file: system/PNG_to_Bin/eu/MOMWILIKE_436x236.png new file: system/PNG_to_Bin/eu/logodata_106x58.bin new file: system/PNG_to_Bin/eu/logodata_382x88.bin new file: system/PNG_to_Bin/eu/logodata_436x236.bin new file: system/babycam/system/bin/logo/logodata_106x58.bin new file: system/babycam/system/bin/logo/logodata_382x88.bin new file: system/babycam/system/bin/logo/logodata_436x236.bin new file: system/babycamEU/system/bin/logo/logodata_106x58.bin new file: system/babycamEU/system/bin/logo/logodata_382x88.bin new file: system/babycamEU/system/bin/logo/logodata_436x236.bin Symbol: 1.修改水印读取方式，便于后期OTA升级维护 Reason: 功能优化 Solution: 功能优化
45 | 2022-06-24 | 胡家乐 | V2.1.1.6 | 运维 | 安抚音播放期间不能调节音量 | [BugFix]No:TLB-master-V2.1.1.6 BugNo: XXXXXX XXXXXX Modifier: Joe Hu Time: 2022/6/24 Modify Files: modified: camera/sample/tuya/demo/src/tuya_ipc_dp_handler.c modified: camera/sample/tuya/demo/src/tuya_ipc_system_control_demo.c modified: camera/sample/tuya/demo/src/user_main.c Symbol: 安抚音播放期间不能调节音量 Reason: 功能优化 Solution: 功能优化
46 | 2022-07-06 | 陈湘杰 | V2.1.1.7 | 运维 | 更新哭声库 | [BugFix]No:TLB-master-V2.1.1.7 BugNo: XXXXXX XXXXXX Modifier: Xiangjie Chen Time: 2022/7/6 Modify Files: modified: ../libs/ingenic/alg/libcryDet_inf.so modified: tuya/demo/src/tuya_ipc_dp_handler.c modified: tuya/demo/src/user_main.c modified: ../../system/babycam/system/lib/libcryDet_inf.so modified: ../../system/babycamEU/system/lib/libcryDet_inf.so Symbol: 更新哭声库 Reason: 功能优化 Solution: 功能优化
47 | 2022-07-08 | 陈湘杰 | V2.1.1.9 | 运维 | 版本号对应发出的测试版本 | [BugFix]No:TLB-master-V2.1.1.9 BugNo: XXXXXX XXXXXX Modifier: Xiangjie Chen Time: 2022/7/6 Modify Files: modified: tuya/demo/src/user_main.c Symbol: 版本号对应发出的测试版本 Reason: 功能优化 Solution: 功能优化
48 | 2022-08-08 | 胡家乐 | V2.1.1.12 | 运维 | 关闭隐私模式推流解决开启隐私模式可能有画面的问题 | [BugFix]No:TLB-master-V2.1.1.12 BugNo: XXXXXX XXXXXX Modifier: Joe Hu Time: 2022/8/8 Modify Files: modified: camera/sample/tuya/demo/src/tuya_ipc_dp_handler.c modified: camera/sample/tuya/demo/src/tuya_ipc_media_demo.c Modified: camera/sample/tuya/demo/src/user_main.c Symbol: 关闭隐私模式推流解决开启隐私模式可能有画面的问题 Reason: 功能优化 Solution: 功能优化
47 | 2022-08-11 | 陈湘杰 | V2.1.1.13 | 运维 | 刷新I帧解决绿屏问题 | [BugFix]No:TLB-master-V2.1.1.13 BugNo: XXXXXX XXXXXX Modifier: Xiangjie Chen Time: 2022/8/11 Modify Files: modified: camera/modules/media/include/lux_video.h modified: camera/modules/media/src/lux_video.c modified: camera/sample/tuya/demo/src/tuya_ipc_dp_handler.c modified: camera/sample/tuya/demo/src/tuya_ipc_media_demo.c modified: camera/sample/tuya/demo/src/tuya_ipc_p2p_demo.c modified: camera/sample/tuya/demo/src/user_main.c Symbol: 刷新I帧解决绿屏问题 Reason: 功能优化 Solution: 功能优化
48 | 2022-08-12 | 胡家乐 | V2.1.1.14 | 运维 | 优化隐私模式开启时录像播放蓝条问题 | [BugFix]No:TLB-master-V2.1.1.14 BugNo: XXXXXX XXXXXX Modifier: Joe Hu Time: 2022/8/12 Modify Files: modified: camera/sample/tuya/demo/src/tuya_ipc_dp_handler.c modified: camera/sample/tuya/demo/src/tuya_ipc_dp_utils.c modified: camera/sample/tuya/demo/src/tuya_ipc_sd_demo.c modified: camera/sample/tuya/demo/src/user_main.c modified: camera/sample/tuya/include/tuya_ipc_stream_storage.h modified: system/PNG_to_Bin/Note_png2bin Symbol: 优化隐私模式开启时录像播放蓝条问题 Reason: 功能优化 Solution: 功能优化
48 | 2022-08-16 | 胡家乐 | V2.1.1.15 | 运维 | 解决存储卡写满问题，不再卸载SD卡 | [BugFix]No:TLB-master-V2.1.1.15 BugNo: XXXXXX XXXXXX Modifier: Joe Hu Time: 2022/8/16 Modify Files: modified: camera/sample/tuya/demo/src/tuya_ipc_dp_handler.c modified: camera/sample/tuya/demo/src/tuya_ipc_dp_utils.c modified: camera/sample/tuya/demo/src/tuya_ipc_sd_demo.c modified: camera/sample/tuya/demo/src/user_main.c modified: camera/sample/tuya/include/tuya_ipc_stream_storage.h modified: system/PNG_to_Bin/Note_png2bin Symbol: 解决存储卡写满问题，不再卸载SD卡 Reason: 功能优化 Solution: 功能优化
48 | 2022-08-17 | 胡家乐 | V2.1.1.16 | 运维 | 优化存储卡无法格式化以及SD卡状态显示异常问题 | [BugFix]No:TLB-master-V2.1.1.16 BugNo: XXXXXX XXXXXX Modifier: Joe Hu Time: 2022/8/17 Modify Files: modified: camera/sample/tuya/demo/src/tuya_ipc_dp_handler.c modified: camera/sample/tuya/demo/src/tuya_ipc_sd_demo.c modified: camera/sample/tuya/demo/src/user_main.c modified: camera/sample/tuya/include/tuya_ipc_stream_storage.h Symbol: 优化存储卡无法格式化以及SD卡状态显示异常问题 Reason: 功能优化 Solution: 功能优化
47 | 2022-08-18 | 陈湘杰 | V2.1.1.17 | 运维 | 优化隐私模式开启时录像播放蓝条问题的方式，提升稳定性 | [BugFix]No:TLB-master-V2.1.1.17 BugNo: XXXXXX XXXXXX Modifier: Xiangjie Chen Time: 2022/8/18 Modify Files: Modified: tuya/demo/src/tuya_ipc_dp_handler.c modified: tuya/demo/src/user_main.c Symbol: 优化隐私模式开启时录像播放蓝条问题的方式，提升稳定性 Reason: 功能优化 Solution: 功能优化
47 | 2022-08-18 | 陈湘杰 | V2.1.1.17 | 运维 | 优化蓝条问题 | [BugFix]No:TLB-master-V2.1.1.17 BugNo: XXXXXX XXXXXX Modifier: Xiangjie Chen Time: 2022/8/18 Modify Files: modified: camera/sample/tuya/demo/src/tuya_ipc_dp_handler.c Modified: camera/sample/tuya/demo/src/tuya_ipc_sd_demo.c Symbol: 优化蓝条问题 Reason: 功能优化 Solution: 功能优化
47 | 2022-09-01 | 陈湘杰 | V2.1.1.18 | 运维 | 改用OSD黑屏遮盖方式优化隐私模式APP拦截画面未成功的问题 | [BugFix]No:TLB-master-V2.1.1.18 BugNo: XXXXXX XXXXXX Modifier: Xiangjie Chen Time: 2022/8/18 Modify Files: Modified: camera/modules/media/include/lux_osd.h modified: camera/modules/media/include/lux_video.h modified: camera/modules/media/src/lux_osd.c modified: camera/modules/media/src/lux_video.c modified: camera/out/media_sample.bin modified: camera/sample/tuya/demo/inc/tuya_ipc_dp_handler.h modified: camera/sample/tuya/demo/src/tuya_ipc_dp_handler.c modified: camera/sample/tuya/demo/src/tuya_ipc_media_demo.c modified: camera/sample/tuya/demo/src/tuya_ipc_sd_demo.c modified: camera/sample/tuya/demo/src/user_main.c modified: camera/sample/tuya/include/tuya_ipc_stream_storage.h Symbol: 改用OSD黑屏遮盖方式优化隐私模式APP拦截画面未成功的问题 Reason: 功能优化 Solution: 功能优化
56 | 2022-10-31 | 徐保权 | V2.1.2 | 运维 | LRDS106图像调试bin合入 | [BugFix]No:TLB-master-V2.1.2 BugNo: XXXXXX XXXXXX Modifier: baouqan xu Time: 2022/10/31 Modify Files: modified: system/babycam/system/etc/sensor/sc4238-t31.bin modified: system/babycamEU/system/etc/sensor/sc4238-t31.bin modified: camera/sample/tuya/demo/src/user_main.c Symbol: LRDS106图像调试bin合入 Reason: 功能优化 Solution: 功能优化
57 | 2022-10-31 | 徐保权 | V2.1.2.1 | 运维 | 修改版本号以供测试 | [BugFix]No:TLB-master-V2.1.2.1 BugNo: XXXXXX XXXXXX Modifier: baoquan xu Time: 2022/10/31 Modify Files: modified: camera/sample/tuya/demo/src/user_main.c Symbol: 修改版本号以供测试 Reason: 功能优化 Solution: 功能优化
58 | 2022-11-08 | 徐保权 | V2.1.3 | 运维 | OTA正式版本2.1.3 | [BugFix]No:TLB-master-V2.1.3 BugNo: XXXXXX XXXXXX Modifier: baoquan xu Time: 2022/11/8 Modify Files: modified: camera/sample/tuya/demo/src/user_main.c Symbol: OTA正式版本2.1.3 Reason: 功能优化 Solution: 功能优化
59 | 2022-11-08 | 徐保权 | V2.1.3.1 | 运维 | bug | [BugFix]No:TLB-master-V2.1.3.1 BugNo: XXXXXX XXXXXX Modifier: baoquan xu Time: 2022/11/8 Modify Files: modified: camera/sample/tuya/demo/src/tuya_ipc_dp_handler.c system/babycam/system/etc/mdev/sd_insert.sh camera/sample/tuya/demo/src/tuya_ipc_system_control_demo.c Symbol: 1，修复PHY启动异常 2，SD卡挂载跳过一场文件 3，指示灯默认不开启 4，单曲播放10-12分钟 Reason: 功能优化 Solution: 功能优化
60 | 2022-12-13 | 陈湘杰 | V2.1.3.2 | 运维 | 算法库更换，使用算法团队提供的人形人脸侦测算法优化人形人脸检测结果 | [BugFix]No:TLB-master-V2.1.3.2 BugNo: XXXXXX XXXXXX Modifier: Xiangjie Chen Time: 2022/12/13 Modify Files: modified: camera/sample/tuya/demo/src/user_main.c modified: camera/libs/ingenic/alg/libjzdl.m.so modified: camera/libs/lux/liblux_faceDet.so modified: camera/libs/lux/liblux_personDet.so modified: system/babycam/system/lib/libjzdl.m.so modified: system/babycam/system/lib/liblux_faceDet.so modified: system/babycam/system/lib/liblux_personDet.so modified: system/babycamEU/system/lib/libjzdl.m.so modified: system/babycamEU/system/lib/liblux_faceDet.so modified: system/babycamEU/system/lib/liblux_personDet.so modified: camera/modules/media/include/cpp/4.7.2/mat.h modified: camera/modules/media/include/cpp/4.7.2/net.h modified: camera/modules/media/include/cpp/4.7.2/utils.h modified: camera/modules/media/include/cpp/lux_faceAlg.h modified: camera/modules/media/include/cpp/lux_faceDet.h modified: camera/modules/media/include/cpp/lux_personAlg.h modified: camera/modules/media/include/cpp/lux_personDet.h modified: camera/modules/media/include/cpp/magik_model_yolov5persondet.mk.h modified: camera/modules/media/include/cpp/post_process.hpp modified: camera/modules/media/include/cpp/yolov5_facedet.mk.h modified: camera/modules/media/include/lux_coverFace.h modified: camera/modules/media/include/lux_fsrc.h modified: camera/modules/media/src/cpp/lux_faceAlg.c modified: camera/modules/media/src/cpp/lux_personAlg.c modified: camera/modules/media/src/lux_coverFace.c modified: camera/modules/media/src/lux_fsrc.c modified: camera/modules/media/src/lux_ivs.c modified: camera/out/media_sample.bin modified: camera/sample/Makefile Symbol: 算法库更换，使用算法团队提供的人形人脸侦测算法优化人形人脸检测结果 Reason: 功能优化 Solution: 功能优化